City of London Corporation’s migration experience – case study

Type of data	Electronic
LLC system software	N/A
Number of charges	23,420

Top 10 lessons learned from City of London Corporation

1. Obtain high level council member and officer support for the migration: it will affect the existing service’s business model.

2. Plan for and resource the data cleansing properly based on knowledge of your data.

3. Data cleansing will need both existing and extra resource.

4. Additional resource will need good project management and IT skills.

5. Data cleansing will be especially challenging in central city areas where the geography is complex and multi-layered.

6. Existing local land charge service levels are likely to be slower if some resource is diverted towards the data cleansing and other preparation processes.

7. Set aside enough time for staff training in the post-migration software and processes.

8. Plan a publicity campaign with regular customers and other originating authorities before migration to smooth the process.

9. Plan for post-migration workload and reduced income stream.

10. Access to online web-based LLC1 searches anytime from anywhere is a bigger advantage to customers than the improved speed of service or cost reductions.

HM Land Registry (HMLR) can put you in touch with the City of London Corporation or HMLR teams if you want to ask further questions: llcproject@landregistry.gov.uk.

Advice for other local authorities

High level support
This is needed because of the implications for the local land charge service’s business model, risks and finances. Reductions in income could jeopardise the existing business model unless costs are also reduced. Temporary reductions in service levels could also occur if some resources are diverted to preparing data for the migration. A significant benefit to the local authority is the removal of the risk where charge registration on HMLR’s LLC Register is by other originating authorities, for example light obstruction notices.

Planning for data cleansing
Good planning of the data cleansing process is critical to timely and successful migration. This is easier if you already have a good understanding of existing data locations, types and quality and therefore the size of the cleansing task. Paper-based systems are likely to need more cleansing due to the absence of automated quality control mechanisms, but errors are also likely in databases and map polygons. For the City of London 9,000 out of 23,000 charges needed corrections.

Resources for data cleansing
These need to be adequate for the size and complexity of the task so test an extract of your data with HMLR. Some local land charge resource will need to be diverted to make use of their subject expertise. Some extra resource will be needed to manage the data cleansing, quality control and IT. The City of London completed data cleansing using the part-time diversion of two staff for about six months.

Skills needed in project management, IT and databases
The potential complexity of the migration project needs additional resource with good project management and IT skills. Perseverance and a methodical approach were needed, and the ability to write and run software scripts to automate local quality checks where possible before uploading datasets to HMLR for formal quality checks.

Central city challenges
The City of London’s complex multi-use, multi-layered, central-city geography set mapping and database challenges not found on suburban housing estates. The solution used was to relate charges to a comprehensive set of digital polygons which reflect the current built form, and which can be archived, adapted or created in the future as that built form changes. Land and property address gazetteers did not provide suitable polygons for spatial searches.

Effect on existing service
Diversion of some local land charge resource to data cleansing and queries will have an adverse effect on the existing service before migration. For the City of London, the Land Charges Team comprised only two people so any diversion would have significant effects. Search turnaround times increased temporarily above the six-day target to about nine days on average.

Staff training and practice
Staff need time to become familiar with the new software and working practices in advance of the actual migration. Registration of new charges with HMLR is quicker and more reliable but we have benefitted from additional scripts written locally to further simplify local data selection for registering and uploading.

Publicity before migration
The local authority needs to publicise in advance the planned migration with its regular customers and with other originating authorities to achieve a smooth migration process with few queries. It also needs to explain that the existing CON29 search process will continue as before. This publicity can be used to promote the area as being open for investment for all who can access the search data available online for the first time on the HMLR website.

Workload and financial implications of migration
After migration there will be a reduction in workload due to the transfer of LLC1 searches, possible reduced demand for CON29 searches and speedier register updates. There will also be reduced search income derived from just the CON29 searches. For the City of London this CON29 search income has so far been sufficient to fund the remaining service. Spare staff capacity created by the migration has so far been used to cleanse other datasets that are used in CON29 searches.

Web-based access is a key benefit for investors
Access to web based LLC1 searches via the HMLR online LLC Register has been a bigger advantage to customers than the improved speed of service or the reduced search costs. Investors considering major acquisitions in the City of London are more interested in the new, online availability of reliable data made possible by the migration, than in small improvements in the time taken or cost of acquiring it.

Who was involved?

City of London Corporation	HM Land Registry LLC Programme
Paul Beckett - Policy and Performance Director (Senior Responsible Officer)	Simon Parker – Delivery Lead
Richard Steele - IT and Corporate GIS Manager (Project manager and data quality controller)	Ben Darling – Business Analyst
Amanda Harcourt - Local Land Charges Officer (LLC expert)

Resolving issues

Complex geography of the City of London
We needed to reflect the complicated geography of a multi-layered, central city area in a comprehensive set of spatial polygons. The eventual solution was to use a long-established set of planning casework polygons to which land charges could be related. In complex areas such as the Barbican mixed-use high-rise estate, some individual addresses continue to be grouped for search purposes.

Devising efficient data cleansing methods
We needed efficient local data cleansing checks to improve data quality as far as reasonable before undergoing HMLR data quality processing. This required local knowledge and good data management skills, including writing local software scripts to automate processes for efficiency.

Balancing existing service provision with preparation for migration
Some reduction in existing service quality is inevitable during the migration preparation phase as limited local land charge expertise is needed for both. We decided to let the existing service slow down to exceed published target turnaround times while data cleansing was given priority. We considered that the longer-term benefits resulting from migration justified the short-term adverse effects.

Publicising and managing the transfer day
Advance publicity was needed for existing regular customers, potential investors in the City of London and other affected parties such as the other originating authorities for some of the local land charges. We alerted all parties to the changes through email, letters, website and a ‘launch’ event in the City of London. For a period up to the migration day all search returns were complemented with publicity material. We also devised a process to handle and complete all searches received just before transfer day and to reject all searches received just after the transfer day.

Planning for reduced workload and income after migration
We estimated that the transfer of LLC1 searches to HMLR could reduce income by about 20% provided that CON29 income remained at previous levels. In practice, CON29 income has been lower than anticipated since autumn 2018 but we don’t yet know whether this is caused by the migration or by wider economic and political uncertainties. At present income levels are still high enough to cover the reduced staff workload costs. Spare staff capacity which resulted from the migration has so far been used to cleanse other datasets that are used in CON29 searches. For example, highway projection licences previously only held in paper files are being checked and scanned for future retrieval in digital form.

Further information

Video: Creating a national LLC Register
Video: How to add, update or cancel charges on the LLC Register using the Maintain service
Video: Searching for local land charges on GOV.UK
Practice Guide 79: Local Land Charges
Infrastructure Act 2015
LLC Act 1975 (as amended)
LLC Rules 2018
LLC Fees (England) Rules 2018
New burdens information
Read our pre-migration guide for more detailed information on preparing your data.

Any questions?

Contact llcproject@landregistry.gov.uk