Key Learnings from Watford Borough Council’s migration experience –

Type of data	Hybrid - paper and digital
LLC system software	Idox Uniform
Number of charges	39,762

Top 10 key learnings from Watford Borough Council

1. For paper records, complete scoping exercises to understand the degree to which they may overlap with other Local Land Charges (LLC) records, particularly digital records.
2. Work to clearly defined timescales agreed by both local authority and HM Land Registry (HMLR).
3. Account for available local authority resource with a visible plan.
4. Make use of technical subject matter experts at HMLR, as they have fantastic knowledge.
5. Be thorough where point data is being used with polygons.
6. When using the Data Analysis Dashboard tool, ensure all involved understand the terminology.
7. When talking with customers during the build up to migration, add a note onto your email signature about upcoming changes.
8. Host weekly catch ups both internally within local authority and externally with HMLR.
9. Run multiple iterations of the Data Analysis Dashboard during migration.
10. Ensure that senior stakeholders in the local authority are aware of progress.

HM Land Registry (HMLR) can put you in touch with Watford Borough Council or HMLR teams if you want to ask further questions: llcproject@landregistry.gov.uk.
Advice for other local authorities

1. For paper records, complete scoping exercises to understand the degree to which they may overlap with other LLC records, particularly digital records. Having scoping exercises completed meant that no discovery time was needed at the beginning of the scan. Involving HMLR’s Transformation Team in scoping to utilise their knowledge sped up this process.

2. Work to clearly defined timescales agreed by both local authority and HMLR. Initially there was a conflict between team priorities and LLC priorities, which meant time allocated to capture varied. By specifying required programme timescales, we were able to overcome this and continue progress.

3. Account for available local authority resource with a visible plan. This meant that all parties were clear on tasks in hand and who was doing them, and that progress was easy to report.

4. Make use of technical subject matter experts at HMLR, as they have fantastic knowledge. This meant there was confidence in referrals from both HMLR Delivery Manager and local authority staff. We recommend ensuring knowledge is shared, so that the pool of technical subject matter experts is increased.

5. Be thorough where point data is being used with polygons. Where the point data fell outside the polygon, it caused spatial failures. This is fixable but can be time consuming.

6. When using the Data Analysis Dashboard tool, ensure all involved understand the terminology. There is the potential for misunderstanding of the task if this isn’t the case. Providing brief descriptions/examples of issues helped everyone understand what was required.

7. When talking with customers during the build up to migration, add a note onto your email signature about upcoming changes. We found this kept migration awareness high among customers. Sending out a group email to our regular personal search customers reinforced go-live message and seems to have been effective as we have received fewer than 10 requests for further information since go-live.

8. Host weekly catch ups both internally within local authority and externally with HMLR. This kept the plan on track with established timescales, and we even feel it could have been implemented earlier internally.

9. Run multiple iterations of the Data Analysis Dashboard during migration. Eight versions of the dashboard were created. It was running our data multiple times that allowed us to identify the best way forwards when improving and migrating our data.

10. Ensure that senior stakeholders in the local authority are aware of progress. Before go-live there was some confusion on the exact state of progress for senior members of the local authority. HMLR will explore the option of sending the letter to the CEO at a specific trigger point, such as when data goes to Quality Gate 2

Read more about who was involved and how they resolved issues.

Who was involved?

Watford Borough Council	HM Land Registry LLC Programme
Lianne Anscombe / Senior LLCO	Simon Parker / Delivery Lead
Sam Oguz / LLCO	Tash Scott / Data Manager
Semeta Bloomfield / Technical Support Team Leader	Andy Short / Business Analyst
	Mark Griffin / Technical Lead

Resolving issues

Quantity and quality of data held
As we held data in every possible format, we had to undertake a digitisation exercise, bringing all versions together. Although this was almost entirely manual, the product of clean, verified data has already proven valuable to the authority.

Communication
There will be a lot of communications during the project. Email alone isn’t good enough at keeping track of all the various threads. Spreadsheets may help, but we would recommend looking at an online collaboration tool, like Microsoft Teams, that could assist multi-channel communications and collaborations.

Final phase before go-live
By this point, everything is speeding up. If you haven’t done so already, then this is the time to make sure your business plans and processes are in place ready for business as usual after go-live. This can be a lengthy project, so also make sure that you know the availability for all involved and have made alternate arrangements if key project members are away for long periods of time.

Further information

Video: Creating a national LLC Register
Video: How to add, update or cancel charges on the LLC Register using the Maintain service
Video: Searching for local land charges on GOV.UK
Practice Guide 79: Local Land Charges
Infrastructure Act 2015
LLC Act 1975 (as amended)
LLC Rules 2018
LLC Fees (England) Rules 2018
New burdens information
Read our pre-migration guide for more detailed information on preparing your data.

Any questions?

Contact llcproject@landregistry.gov.uk